APOLLO ADVANCEMENT

Development Audit

& Strategic Plan

Proposal for Maryvale Academy of Ottawa

Prepared by John Jalsevac, PhD

Apollo Advancement

April 2026

Executive Summary

Maryvale Academy has reached an inflection point. After nearly two decades of steady growth as an independent Catholic school, the board has rightly identified the need to secure a permanent home through a $5 million capital campaign. This is a significant and exciting step, but it also carries significant risk if the fundraising infrastructure is not in place to support it.

A development audit is the essential first step. Before launching any campaign, an organization needs a clear, honest picture of its current fundraising capacity: what is working, what is missing, and what must be built before major donor solicitation begins. This proposal outlines the scope, methodology, timeline, deliverables, and investment for a comprehensive development audit and strategic plan for Maryvale Academy.

The audit will assess Maryvale's fundraising culture, board engagement, donor data, communications, stewardship practices, and campaign readiness. The result will be a prioritized roadmap that positions the school to pursue its capital campaign with confidence, credibility, and a realistic understanding of what success will require.

Context

Maryvale Academy of Ottawa is an independent Catholic school serving students from Junior Kindergarten through Grade 8. Founded approximately 20 years ago, the school has grown steadily and now employs 13 full-time staff. Maryvale offers a classically-based curriculum with a strong French program and a Sacred Music Choir, distinguished by its commitment to daily adoration, weekly Mass, and authentically Catholic formation.

Despite this growth, Maryvale has never owned a building. In its 19 years of operation, it has reported $0 in land and buildings on its CRA filings, paying an estimated $1.8 million in cumulative rent with no equity to show for it. The board has identified a $5 million capital campaign as the path to a permanent facility.

This is the right goal. But a capital campaign of this scale requires more than ambition. It requires a development infrastructure that can identify, cultivate, and steward major donors over a multi-year period. The audit will determine whether that infrastructure exists, and if not, what needs to be built before the campaign can proceed effectively.

Scope of Work

The development audit is a comprehensive assessment of Maryvale Academy's fundraising capacity, organizational culture, and campaign readiness. It is not a compliance exercise. It is a diagnostic of the beliefs, systems, and relationships that drive (or inhibit) philanthropic investment.

The audit will examine seven core areas:

| Organizational Culture | How the school thinks and talks about fundraising; whether development is seen as a shared responsibility or an uncomfortable necessity |
| --- | --- |
| Board Engagement | Board members' understanding of their fundraising role, personal giving, willingness to open doors, and capacity for campaign leadership |
| Donor Data & Systems | Quality and completeness of donor records; CRM usage; segmentation; ability to track giving history, lapsed donors, and prospects |
| Communications & Storytelling | Appeal letters, newsletters, impact reports, case for support, website, social media; whether the school is telling a compelling, consistent story |
| Fundraising Programs | Current revenue streams, annual fund structure, events, major gifts, grants, planned giving; diversification and sustainability |
| Donor Stewardship | Acknowledgment practices, recognition, reporting, relationship management; whether donors feel valued and informed |
| Campaign Readiness | Feasibility of the $5M capital campaign; donor base depth, leadership gift potential, case strength, board capacity, and organizational discipline |

Capital campaign readiness receives particular emphasis in this engagement. The audit will assess whether the school has the donor base, board capacity, case for support, and organizational discipline to sustain a multi-year, multi-million-dollar campaign, and will identify specific gaps that must be addressed before a quiet phase can begin.

Methodology

The audit follows a four-phase process designed to move from data collection through analysis to actionable recommendations. Total engagement timeline: 6 to 8 weeks from receipt of initial documents.

| Phase | Timeline | Focus | Activities |
| --- | --- | --- | --- |
| Phase 1 | Weeks 1-2 | Document & Data Collection | Gather financial statements, donor data exports, communications samples, board rosters, and governance documents. Issue stakeholder interview invitations. Begin preliminary analysis of T3010 filings and CRA data. |
| Phase 2 | Weeks 2-3 | On-Site Discovery | Two-day visit to Ottawa for stakeholder interviews, campus tour, and board working session. This phase generates the qualitative insights that give the quantitative data its meaning. |
| Phase 3 | Weeks 3-5 | Analysis & Benchmarking | Analyze donor retention, giving patterns, revenue diversification, cost-per-dollar-raised, and peer benchmarks. Synthesize interview findings with data analysis. Identify patterns, gaps, and opportunities. |
| Phase 4 | Weeks 6-8 | Report & Presentation | Draft written report and strategic plan. Review with primary contact for factual accuracy. Deliver final report and present findings to the board in person or via video. |

On-Site Visit

A two-day on-site visit to Ottawa is included in this engagement. The visit serves three purposes that cannot be replicated remotely:

- Stakeholder interviews. One-on-one conversations with board members, the executive director, key staff, and (where appropriate) select donors or volunteers. These interviews are the most diagnostic element of the audit. How people talk about fundraising reveals far more than any spreadsheet.

- Campus visit. Seeing the current facility, understanding the daily experience of families and staff, and assessing what the school communicates through its physical environment. This is essential context for evaluating the capital campaign case.

- Board working session. A 60- to 90-minute session with the full board to present initial observations, test assumptions, and begin aligning around priorities. This is not the final presentation; it is a collaborative diagnostic conversation.

Deliverables

Upon completion of the audit, Maryvale Academy will receive:

- Written Audit Report. A comprehensive document presenting findings across all seven audit areas, with specific observations, benchmarks, and prioritized recommendations. This is not a generic template; every finding will be specific to Maryvale.

- Strategic Development Plan. A phased implementation roadmap with clear milestones, responsibilities, and timelines. The plan will address both immediate capacity-building and longer-term campaign preparation.

- Board Presentation. An in-person presentation of findings and recommendations to the full board (or a designated committee). This presentation is designed to build alignment and commitment, not just convey information.

- 30-Day Follow-Up. One follow-up call 30 days after the board presentation to answer questions, troubleshoot early implementation, and provide additional guidance as needed.

Timeline

| Engagement signed | Week 0 |
| --- | --- |
| Document and data request issued | Week 0 |
| Initial documents received | Week 1 |
| On-site visit (Ottawa, 2 days) | Weeks 2-3 |
| Analysis and benchmarking | Weeks 3-5 |
| Draft report to primary contact for review | Week 6 |
| Final report delivered | Week 7 |
| Board presentation | Week 7-8 |
| 30-day follow-up call | Week 11-12 |

Note: The timeline begins upon receipt of the initial document package. Delays in document delivery will extend the overall timeline proportionally.

Investment

The following table summarizes the total investment for this engagement, including all professional fees and travel expenses for the two-day on-site visit in Ottawa.

| Professional Fees |  |  |
| --- | --- | --- |
| Development audit and strategic plan |  | $7,500 |
| Board presentation (in-person or virtual) |  | Included |
| 30-day follow-up consultation |  | Included |
| Travel Expenses (Ottawa, 2 days) |  |  |
| Mileage (Kawartha Lakes to Ottawa, return: ~700 km at CRA rate) |  | $504 |
| Accommodation (1 night) |  | $200 |
| Meals (2 days) |  | $100 |
| Parking and incidentals |  | $50 |
| Total Investment |  | $8,354 |

Payment terms: 50% due upon signing of the engagement letter; 50% due upon delivery of the final written report. Travel expenses are included in the fixed fee and will not be invoiced separately.

What is not included: Implementation of audit recommendations, ongoing fundraising counsel, campaign management, or additional on-site visits beyond the two days specified. These services are available through Apollo Advancement's fractional development leadership and campaign consulting engagements, and can be discussed following the audit.

About Apollo Advancement

Apollo Advancement is a fundraising consulting practice serving arts, education, and community nonprofits across Canada and the United States. Founded by John Jalsevac, PhD, the practice is built on a simple conviction: fundraising results follow from shifting organizational beliefs, not implementing tactics.

Relevant experience:

- Wayside Academy. As Headmaster, grew annual revenue from approximately $280K to over $600K and expanded the donor base from under 50 to more than 300 donors in a single year. Secured multiple major gifts including $150K and several $100K commitments.

- Peterborough Singers. Serving as Campaign Director for a $250K legacy fund. Grew the donor base from 80 to 325 donors and reached the $100K milestone within the first phase.

- LifeSiteNews. As Managing Director, scaled web traffic 810%, grew social media from 0 to 600,000+ followers, expanded the email list from 30,000 to 500,000+, and managed a budget of approximately $2M with up to 30 staff.

John holds a PhD in Philosophy from the University of Toronto (Centre for Medieval Studies, 4.0 GPA) and brings a distinctive combination of intellectual rigor, communications expertise, and hands-on fundraising experience. He has been a member of the Peterborough Singers for 15 years.

Next Steps

If this proposal is acceptable, the next steps are straightforward:

- Engagement letter. Apollo Advancement will prepare a brief engagement letter formalizing the scope, timeline, and payment terms outlined in this proposal.

- Document request. Upon signing, Maryvale will receive a detailed list of documents and data to compile. The speed and completeness of this initial response is itself a useful early indicator.

- Scheduling. We will coordinate dates for the two-day on-site visit in Ottawa, ideally within the first two weeks of the engagement.

I look forward to working with the Maryvale board to build the foundation for a successful campaign.

John Jalsevac, PhD

Apollo Advancement  |  Kawartha Lakes, Ontario

(705) 313-1588  |  jjalsevac@gmail.com

apolloadvancement.com